LICEUL DE ARTĂ SIBIU                                                                                                                                                                                                   STR. AL. ODOBESCU NR.2

TEL. 211458, FAX: 213149

„ART ACHIEVES NEW EUROPE”

Coordination:

ITALY I.I.S.S. “E. Giannelli”

Partners: Estonia, Czech Rep., Romania and Turkey

Romanian activities for- Estonian mobility-Tallinn 17-23.11.2018

- Counseling and informing reunion for interschool exchange project organised by The National Agency in Romania, Bucharest, 21.09.2018

- Creating the Coordinating team

- coordinator of the project: Graphic art teacher Anca Ioana Serfozo

- evaluation manager: Sculpture teacher Ioan Candea

- students committee that will actively participate in the management and evaluation of the planned activities: all the students who participate in the mobilities

- operative group composed of foreign languages, mother tongue, art, technical laboratories, history and art history teachers:

- foreign languages: English teacher Nicoleta Faghi

visual art: - painting teachers: Marcela Froman and Eugen Dornescu

- sculpture teacher: Ioan Cândea and Crina Fetecau

- art history teachers: Marius David and Bianca Florea

- graphic art teachers: Anca Ioana Serfozo and Andrei Szabo

- technical laboratories: music teacher Andrei Craciun

- accountant: Aurelia Solomon

- Art department staff meeting: 09.10.2018

- Presentation of the AR.AC.N.E project

- Establishing criteria for students and teacher selection for all mobilities

- Project dissemination among students; Presentation of criteria for student selection

-10th grade students

-11th grade students

-12th grade students

- Evaluations of enlisted students on all criteria:

- AR.AC.N.E. Logo: sculpture teacher Ioan Cândea, painting teacher Marcela Mihaela Froman and graphic art teacher Anca Ioana Serfozo

- letter of application written in English language: English teacher Nicoleta Faghi

- accuracy data for the rest of the criteria: headmaster Daniela Ioana Sacarelis, graphic art teacher Anca Ioana Serfozo and  11th grade student Alfred Andreas Schuller

- Publishing final results after the evaluations

- Selected students and teachers staff meeting

- Presentation of the Estonian mobility activities

- Logo election

- deciding the work of art to be presented in Tallinn as a step by step process: step by step decorative painting

- filming the step by step process: documentation in Astra Museum of Traditional Civilization; filming the step by step painting process - 5 students selected for the mobility

- video and sound effects -music teacher Andrei Craciun

- digital formatting the elected logo for AR.AC.N.E.-graphic art teacher Andrei Szabo

- creating the dissemination project visual space  inside the school- project coordinator teacher Anca Ioana Serfozo

- Selected students and teachers staff meeting

- dissemination of Estonian culture and history after individual research done by students

- parents and students school meeting for the mobility

- traveling formalities for students and  teachers -project coordinator teacher  Anca Ioana Serfozo

- communication with the partner countries -headmaster Daniela Ioana Sacarelis and project coordinator teacher  Anca Ioana Serfozo

- project budget management-accountant Solomon Aurelia, headmaster Daniela Ioana Sacarelis and project coordinator teacher Anca Ioana Serfozo

Romanian activities for Czech Republic  mobility, Vysoke Myto 4-8.03.2019

- AR.AC.N.E. Project dissemination (Estonia, Tallinn mobility 17-23.11.2018) – Art department staff meeting:

AR.AC.N.E. Project dissemination (Estonia, Tallinn mobility 17-23.11.2018 )- among students as a preparation for the next mobility selection.

-10th grade students

-11th grade students

-12th grade students

- Pedagogical committee staff meeting -the theme: Ways of stimulating creativity in students through Erasmus+ Project AR.AC.N.E. Estonian mobility activity analysis for the participating students.

- School website AR.AC.N.E. Project dissemination

- Project dissemination among students; Presentation of criteria for student selection:

-10th grade students

-11th grade students

-12th grade students

- Evaluations of enlisted students on all criteria:

- Composition inspired by the creation of the Czech artist Frantisek Kupka: sculpture teacher Ioan Cândea, painting teacher Marcela Mihaela Froman and graphic art teacher Anca Ioana Serfozo

- letter of application written in English language: English teacher Nicoleta Faghi

- accuracy data for the rest of the criteria: headmaster Sacarelis Daniela Ioana, graphic art teacher Anca Ioana Serfozo and  12th grade student Raluca Maria Stănilă

- Publishing Final results after the evaluations

- Selected students and teachers staff meeting

- presentation of the Czech Republic mobility activities

- deciding the work of art to be presented in Vysoke Myto as a step by step process: step by step mixed media on canvas

- filming the step by step process: documentation in the graphic department studio by means of photography. Students have been photographed by their colleagues in attitudes that represent their unique personalities -8 students selected for the mobility; creation of the mixed media composition on canvas.

- film montage and sound effects-music teacher Andrei Craciun

- Selected students and teachers staff meeting

- dissemination of Czech Republic culture and history after individual research done by students

- parents and students school meeting for the mobility

- traveling formalities for students and  teachers-project coordinator teacher  Anca Ioana Serfozo

- communication with the partner countries-headmaster Daniela Ioana Sacarelis and project coordinator teacher  Anca Ioana Serfozo

- project budget management-accountant Solomon Aurelia headmaster Daniela Ioana  Sacarelis and project coordinator teacher  Anca Ioana Serfozo

Romanian activities for- Turkish  mobility-Gaziantep 20-24.05.2019

- posting images and videos on the project Facebook page and  Instagram

- AR.AC.N.E. Project dissemination (Czech Republic, Vysoke Myto mobility4-8.03.2019) –Art department staff meeting

- AR.AC.N.E. Project dissemination (Estonia, Tallinn and Czech Republic Vysoke Myto mobility) opened to all students and teachers in the school during the week dedicated to: A Different Type of Schooling

- Students committee staff meeting

- discussions about the main expected achievements of the AR.AC.N.E Project

- creating a digital data base with photographs and videos from the mobilities in Estonia and Czech republic to be used as inspiration for new and original artistic creations

- students have decided that the Art museums that  they visited in Estonia and Czech Republic are perfect subjects of inspiration for new and original art creations.

- students expressed the desire to create works of art inspired from the Jewelry museum in Tallinn, Visoke Myto Art Galery, Karosa Museum, Kampa museum and Dox Galery as their way to honor each host country

- the works of art created by the students from all the art departments: sculpture, painting and graphic arts are to be presented in Turkey

- Teacher selection for the mobility: sculpture teacher Crina Fetecău Oprean, visual art teacher Bianca Maria Florea and English teacher Nicoleta Faghi

- AR.AC.N.E. Project dissemination (Estonia, Tallinn and Czech Republic Vysoke Myto mobility) – for the Romanian teachers participating in the Turkish mobility

- AR.AC.N.E. Project dissemination in local newspaper.

- travelling formalities for teachers-project coordinator teacher  Anca Ioana Serfozo

- communication with the partner countries-headmaster Daniela Ioana Sacarelis, English teacher Nicoleta Faghi and project coordinator teacher  Anca Ioana Serfozo

- project budget management-accountant Solomon Aurelia headmaster  Daniela Ioana Sacarelis and project coordinator teacher Anca Ioana Serfozo